Table of Contents

# 1	LaaS Platform — Critical Failure Point Analysis

This document identifies potential failure points, missing considerations, and critical dependencies that could derail the project if not addressed proactively.

## 1.1	1. LICENSING & LEGAL

### 1.1.1	🔴 CRITICAL: Software Licensing

| Software | Current Status | Action Required |
| --- | --- | --- |
| MATLAB | ❌ NOT RESOLVED | Must procure Concurrent/Campus-Wide Network License from MathWorks. Per-seat license is NOT valid for multi-user hosting |
| AutoCAD | ⚠️ Needs audit | Requires Autodesk multi-user server subscription |
| Blender | ✅ OK | Free and open-source |
| CUDA Toolkit | ✅ OK | Free from NVIDIA |
| Other ISV Software | ⚠️ Needs audit | Review each vendor’s licensing terms for shared hosting |

### 1.1.2	🟡 Legal & Compliance Gaps

| Item | Status | Notes |
| --- | --- | --- |
| Terms of Service | ❌ Missing | Must define user agreements, liability, SLA |
| Privacy Policy | ❌ Missing | Required for DPDPA 2023 compliance |
| GST Registration | ⚠️ Need clarification | India: Need GST for charging users |
| Payment Gateway Merchant Account | ❌ Need to procure | Razorpay/Stripe require business registration |
| Domain Registration | ❌ Need to secure | lab.youragency.in or similar |

## 1.2	2. INFRASTRUCTURE PROCUREMENT GAPS

### 1.2.1	🟠 Missing from Current List

| Item | Estimated Cost | Priority |
| --- | --- | --- |
| Server Rack/Cabinet | ₹15,000–30,000 | HIGH |
| Cat6a/Cat7 Cables for networking | ₹3,000–5,000 | MEDIUM |
| KVM Switch | ₹5,000–10,000 | MEDIUM |
| IPMI/Out-of-Band Management | Already on ASUS board | ✅ OK |
| Additional SSD for Docker registry | ₹5,000–8,000 | MEDIUM |
| Backup Internet Line | ₹5,000–10,000/month | HIGH |

### 1.2.2	🟠 Physical Environment

| Item | Status | Notes |
| --- | --- | --- |
| Dedicated Room | ⚠️ Need to confirm | Requires lockable server room |
| Cooling (AC) | ⚠️ Need to install | 3-4kW continuous heat load |
| Power Infrastructure | ⚠️ Need to verify | Can handle 4kW + UPS charging |
| Fire Suppression | ⚠️ Recommended | Consider ABC extinguishers |
| Physical Security | ⚠️ Need access control | Lock, CCTV recommended |

## 1.3	3. SOFTWARE INTEGRATIONS — MISSING DEPENDENCIES

### 1.3.1	🔴 Critical Integrations Not in Current Doc

| Service | Purpose | Status |
| --- | --- | --- |
| SMTP Provider | Transactional emails (verification, receipts) | ❌ Missing |
| SMS Gateway | OTP, notifications | ❌ Missing |
| Push Notifications | Web push for alerts | ❌ Missing |
| Video Conferencing SDK | Mentorship sessions (Jitsi/Zoom) | ⚠️ Need to decide |
| Container Registry | Store base Docker images | ❌ Missing solution |
| Backup Service | Database backup | ❌ Missing |

### 1.3.2	🟠 Third-Party Subscriptions Required

| Service | Monthly Cost (Est.) | Alternative |
| --- | --- | --- |
| Cloudflare Pro | ₹2,000–5,000/mo | Free tier limited |
| Razorpay/Stripe | 2% transaction fee | Stripe (2.9% + fixed) |
| SMTP (SendGrid/SES) | ₹1,000–3,000/mo | Self-hosted (Postfix) |
| SMS (Twilio/Msg91) | ₹2,000–5,000/mo | — |
| Monitoring Alerts | ₹0–2,000/mo | Free tiers exist |
| Domain (.in/.com) | ₹500–1,000/yr | — |
| SSL Certificate | ₹0 (Let’s Encrypt) | ✅ Free |

### 1.3.3	🟡 Decision Required

| Decision | Options | Recommendation |
| --- | --- | --- |
| Video Conferencing | Jitsi (self-hosted) vs Zoom SDK | Jitsi for cost, Zoom for reliability |
| Email Delivery | SendGrid/SES vs Postfix on NAS | Postfix for control |
| Container Registry | Local (on NAS) vs Docker Hub vs GHCR | Local on NAS for speed |
| Monitoring | Prometheus self-hosted vs cloud | Prometheus + Grafana (free) |

## 1.4	4. TECHNICAL ARCHITECTURE GAPS

### 1.4.1	🟠 Missing Components

| Gap | Impact | Solution |
| --- | --- | --- |
| Docker Registry | Can’t distribute base images | Set up local registry on NAS or use GitHub Container Registry |
| Image Update Pipeline | No way to update base software | CI/CD pipeline to rebuild and push images |
| Database Backup | Data loss risk | Automated pg_dump to NAS |
| Redis Persistence | Session state loss on crash | Redis RDB/AOF persistence |
| Log Aggregation | Can’t debug issues | ELK Stack or Loki + Grafana |
| Service Discovery | How nodes find each other | Consul, etcd, or static config |

### 1.4.2	🟠 Base Image Build Pipeline

The current plan mentions building a custom Docker image but doesn’t detail HOW:

| Step | Tool | Notes |
| --- | --- | --- |
| Build | Docker BuildKit | Enable cache sharing |
| Store | Local Registry | On NAS over 10GbE |
| Test | CI pipeline | Automated smoke tests |
| Deploy | Pull to nodes | Automated or manual |
| Rollback | Version tags | Keep v1, v2, etc. |

## 1.5	5. OPERATIONAL GAPS

### 1.5.1	🔴 Missing Operational Capabilities

| Gap | Risk | Recommendation |
| --- | --- | --- |
| 24/7 Support | Users stranded at night | Define SLA, consider outsourced support |
| On-call Rotation | Slow incident response | Implement PagerDuty or similar |
| Incident Response Plan | No process when things break | Document runbooks |
| User Documentation | Support ticket flood | Create wiki/knowledge base |
| Admin Training | Can’t manage platform | Train internal team before launch |
| Runbook | No deployment procedures | Document every procedure |

### 1.5.2	🟠 Monitoring & Observability Gaps

| What to Monitor | Current Status | Gaps |
| --- | --- | --- |
| Node health | ✅ Covered (DCGM) | No alerting defined |
| Container health | ⚠️ Partial | Need container-level monitoring |
| API health | ⚠️ Partial | Need uptime checks |
| User activity | ❌ Missing | Need audit logging |
| Billing accuracy | ❌ Missing | Need reconciliation |
| Disk space | ⚠️ Need automation | Auto-cleanup not defined |

## 1.6	6. TIMELINE RISKS

### 1.6.1	🔴 Critical Path Items

| Task | Dependency | Risk |
| --- | --- | --- |
| MATLAB license procurement | MathWorks response time | HIGH — Could take weeks |
| ISP installation | Local ISP | HIGH — Could take 2-4 weeks |
| Hardware delivery | Vendor lead times | MEDIUM |
| Keycloak setup | University cooperation | MEDIUM — Need SSO federation |
| Payment gateway approval | Business docs | HIGH — Could take 1-2 weeks |

### 1.6.2	⚠️ Manager’s 1-Week Timeline Risk

The Manager wants delivery by March 7, 2026. This is HIGHLY UNREALISTIC because:

| Reason | Impact |
| --- | --- |
| Hardware not procured | 2-4 weeks delivery |
| Infrastructure not set up | 8-12 weeks (Phases 0-1) |
| Software MVP needs development | 1-2 weeks (if cloud-hosted) |
| Payment integration needs approval | 1-2 weeks |
| University SSO needs coordination | 2-4 weeks |

Recommendation: Communicate realistic timeline to Manager. MVP (web portal only) possible in 1 week, but full platform (with infrastructure) takes 12+ weeks.

## 1.7	7. USER MANAGEMENT GAPS

### 1.7.1	🟠 Missing User Features

| Feature | Priority | Notes |
| --- | --- | --- |
| Password Reset | HIGH | Required for all users |
| Email Verification | HIGH | Before account activation |
| Session Timeout | HIGH | Auto-logout idle users |
| Two-Factor Auth | MEDIUM | For admin accounts minimum |
| Profile Picture | LOW | Optional |
| Notification Preferences | MEDIUM | Email/SMS/Push settings |

### 1.7.2	🟠 University SSO Complexity

The plan mentions Keycloak with university SSO federation, but:

| Challenge | Details |
| --- | --- |
| University IT Cooperation | Need access to their IdP |
| Multiple Universities | Each may have different IdP |
| Public Users | Google OAuth is simpler |
| Attribute Mapping | How to map university groups to roles? |

## 1.8	8. BILLING & PAYMENT GAPS

### 1.8.1	🔴 Critical Gaps

| Gap | Issue | Solution |
| --- | --- | --- |
| Merchant Account | Need business registration | Razorpay requires GST, bank account |
| GST Invoicing | Legal requirement in India | Generate GST-compliant invoices |
| Refund Policy | Not defined | Must document |
| Wallet Minimum Balance | Prevent negative balance | Auto-debit with threshold |
| Subscription Tiers | Bronze/Silver/Gold defined but not implemented | Need plan management |

### 1.8.2	🟠 Pricing Model Complexity

| Consideration | Status |
| --- | --- |
| Per-minute vs per-hour billing | Need decision |
| Idle time charges | What counts as “used”? |
| Session pause/resume | Complex to implement |
| Overage charges | What if user exceeds booked time? |
| Free tier (Freemium) | How funded? |

## 1.9	9. SECURITY GAPS

### 1.9.1	🟠 Missing Security Measures

| Measure | Priority | Implementation |
| --- | --- | --- |
| Rate Limiting | HIGH | On API gateway |
| DDoS Protection | HIGH | Cloudflare (covered) |
| SQL Injection Protection | HIGH | ORM + validation |
| XSS Protection | HIGH | Sanitization |
| CSRF Tokens | HIGH | Next.js + backend |
| Input Validation | HIGH | All user inputs |
| Audit Logging | MEDIUM | All admin actions |
| Encryption at Rest | MEDIUM | LUKS on NAS |
| Network Segmentation | HIGH | VLANs (covered) |

### 1.9.2	🟠 Access Control Gaps

| Concern | Status |
| --- | --- |
| Admin access to user sessions | Need audit trail |
| Support staff access levels | Define roles |
| API key management | Need rotation policy |
| SSH key management | For on-premises access |

## 1.10	10. NETWORKING GAPS

### 1.10.1	🟠 Missing Details

| Item | Status | Notes |
| --- | --- | --- |
| Static IP | Need from ISP | For DNS + Cloudflare |
| Reverse DNS | Need to configure | For email deliverability |
| Firewall Rules | Need documentation | For each service |
| NAT Configuration | Need to document | Cloudflare Tunnel |
| Load Balancing | Not covered | Consider for future scaling |

## 1.11	11. FAILURE SCENARIOS — CRITICAL THINKING

### 1.11.1	Scenario 1: GPU Fault Causes Multiple Session Crashes

Likelihood: Medium (during heavy GPU usage)

Impact: 4+ users lose work, support tickets flood in

Current Mitigation: MPS watchdog, 30-60s auto-restart

What’s Missing: - User notification system (email/SMS) - Status page to communicate issues - Compensation policy for affected users - Escalation procedure for support team

### 1.11.2	Scenario 2: NAS Goes Down

Likelihood: Low (hardware failure)

Impact: All users lose access to files, platform unusable

Current Mitigation: ZFS snapshots on NAS

What’s Missing: - Backup NAS or cold spare - Procedure to restore from snapshot - Alternative storage for new sessions (can’t start without NAS) - Communication plan for users

### 1.11.3	Scenario 3: Internet Outage During Business Hours

Likelihood: Medium (ISP issues)

Impact: Platform offline, no revenue, user complaints

Current Mitigation: Dual ISP recommended but not implemented

What’s Missing: - Second ISP contracted - Automatic failover configured - Uptime SLA defined (is this covered?)

### 1.11.4	Scenario 4: MATLAB License Server Down

Likelihood: Medium

Impact: Users can’t use MATLAB, support tickets

What’s Missing: - License failover (if MathWorks supports) - Alternative software notification - Credit/refund policy for affected time

### 1.11.5	Scenario 5: Database Corruption

Likelihood: Low

Impact: User accounts, bookings, billing data lost

Current Mitigation: None mentioned

What’s Missing: - PostgreSQL automated backups - Point-in-time recovery - Regular backup restore testing - Offsite backup location

### 1.11.6	Scenario 6: Billing Calculation Error

Likelihood: Medium (complexity)

Impact: Revenue leakage or overcharging users

What’s Missing: - Billing reconciliation reports - Audit of billing calculations - User-facing usage history - Dispute resolution process

## 1.12	12. RECOMMENDED ACTION ITEMS

### 1.12.1	Immediate (This Week)

| Priority | Action | Owner |
| --- | --- | --- |
| 🔴 | Contact MathWorks for MATLAB network license | Procurement |
| 🔴 | Verify ISP can provide 500Mbps+ symmetric | Procurement |
| 🔴 | Secure domain name | DevOps |
| 🔴 | Begin merchant account application (Razorpay) | Finance |
| 🟠 | Define Terms of Service & Privacy Policy | Legal |
| 🟠 | Confirm server room/cooling exists | Facilities |

### 1.12.2	Before Phase 0

| Priority | Action | Owner |
| --- | --- | --- |
| 🟠 | Procure all hardware (NICs, switch, NAS, UPS) | Procurement |
| 🟠 | Install cooling infrastructure | Facilities |
| 🟠 | Set up SMTP for transactional emails | DevOps |
| 🟠 | Decide on video conferencing solution | Product |
| 🟠 | Audit all software licenses | Legal |

### 1.12.3	Before Software Development

| Priority | Action | Owner |
| --- | --- | --- |
| 🟡 | Set up GitHub/GitLab repository | DevOps |
| 🟡 | Define CI/CD pipeline | DevOps |
| 🟡 | Set up staging environment | DevOps |
| 🟡 | Create API documentation standards | Tech Lead |

## 1.13	13. QUESTIONS FOR CLARIFICATION

- University SSO: Have you contacted KSRCE IT about Keycloak federation?

- Multiple Universities: Will this platform serve multiple universities or just KSRCE initially?

- Public Users: How will you verify identity for public users (no university email)?

- Revenue Model: Who pays for freemium tier — university or platform?

- Support Model: Will there be dedicated support staff?

- Legal Entity: Is the company registered for GST and business?

- Data Center: Where will the machines be physically located?

- Power Backup: How long should UPS sustain the platform?

- Acceptable Downtime: What’s the SLA you’re committing to?

- Incident Response: Who’s on-call for critical issues?

## 1.14	Summary

| Category | Critical Gaps | High Priority | Medium Priority |
| --- | --- | --- | --- |
| Licensing | MATLAB, AutoCAD | Terms of Service | Software audit |
| Procurement | — | Hardware, UPS, Cooling | Rack, Cables |
| Integrations | SMTP, SMS, Payment Gateway | Container Registry | Push Notifications |
| Operations | Support team, Documentation | Monitoring, Alerts | Backup automation |
| Timeline | Unrealistic 1-week goal | — | — |
| Security | Access control audit | Rate limiting | Encryption at rest |

This analysis should be reviewed with stakeholders to prioritize addressing these gaps before launch.